## Slide 1: Online Medical Certification System (OMCS) Project Approach
September 2013

## Slide 2
Key Project Driver
Determine whether the Online Medical Certification System has the potential to reduce costs involved in the certification process while, at the same time, improving access to the system and the quality of information recorded.
The Government has brought the challenge of managing ICT front and centre. We are serious about providing better, faster and more secure services to New Zealanders. This requires a strong move towards online services, better protection of New Zealanders’ private information, more collaboration between government departments, and a change in public service culture.
Our Better Public Services challenges include two which focus on public sector ICT:
  - New Zealand businesses have a one-stop shop for all government support and advice they need to run and grow their business (Result 9); and
  - New Zealanders can complete their transactions easily with government in a digital environment (Result 10).
  Extract from Government ICT Strategy and Action Plan to 2017, Foreword by Hon Chris Tremain, Minister of Internal Affairs

## Slide 3: Project Purpose
Develop an indicative business case to provide decision makers an early indication of the way forward.
Project Outcome
An indicative business case that will inform decision making and seek early approval to develop the investment proposal further
Defined business, user and regulatory requirements for an online medical certification system and associated processes for use by various stakeholders
Identified efficiency and quality gains that would be delivered by the online medical certification system
A request for information (RFI) process that will confirm indicative costs, risks and time scales from vendor responses
Fit for purpose assessment of medical certification systems in use within the government sector for evaluating options

## Slide 4: Project Approach - Discussion
REQUIREMENTS
Identify business, user and regulatory requirements of the existing business processes
Review previous business, user and regulatory requirements and consider if they are still relevance and/or appropriateness
Identify business, user and regulatory requirements in the context of anticipated efficiency and quality gains and goals of the to-be business processes
Consolidate requirements and prioritise them as mandatory, desirable, option or future enhancement
Validate requirements with stakeholder groups (first internally then externally)
Seek approval of requirements
EFFICIENCY & QUALITY GAINS
Identify investment objectives i.e. anticipated efficiency and quality gains
Review proposed changes to the business process in the context of identified opportunities /requirements for anticipated efficiency and quality gains
Review previous cost benefit justifications or investment logic mapping and consider relevance and appropriateness
Identify expected benefits (financial and non financial) that will be claimed by the project after completion
Validate expected benefits with stakeholder groups
Assess costs, risks and dependencies
Appraise investment against key critical success factors

## Slide 5: Project Approach – Discussion (Continued)
  REQUEST FOR INFORMATION (RFI)
  A RFI is a standard business process whose purpose is to collect written information about the capabilities of various suppliers.
Identify information and process requirements to develop a RFI in conjunction with Corporate services (i.e. MIS and Procurement)
Develop the RFI taking into consideration:
  Background information, instructions and conditions for responding to this RFI
  Conditions and requirements of this RFI process, together with the evaluation process and criteria
  Information required from vendors when they respond to the RFI
  Government rules of sourcing
Seek Project Executive approval after RFI is reviewed by Corporate services (i.e. MIS and Procurement)
Initiate the RFI process
Consolidate and review vendor response
Confirm indicative costs, risks and time frames from vendor responses
FIT FOR PURPOSE ASSESSMENT
Review previous fit for purpose assessments (if undertaken) and develop a fit for purpose process and assessment questionnaire
Review the fit for purpose process and assessment questionnaire with procurement to ensure that it does not compromise the RFI process
Identify a target group of agencies that have a medical certification process and maybe willing to participate in the fit for purpose assessment
Select a sample number of agencies within the government sector who consent to participate in the fit for purpose assessment
Initiate the fit for purpose assessment
Consolidate and review findings from the assessment

## Slide 6
INDICATIVE BUSINESS CASE
Develop the indicative business case by analysing the following aspects:
  Strategic case : Where are we now and where do we want to be ?
  Economic case : What is the best value for money option for getting us there ?
  Commercial case : What do we need to procure to help us get there ?
  Financial case : Can we afford to get there and how will we fund it?
  Management case: How do we ensure we get there ? How will we know if we succeed?
Recommend an indicative way forward with a limited number of short‐listed options for further detailed analysis
Note: Business and user requirements, efficiency and quality gains , fit for purpose assessment and the request for information (RFI) will inform the indicative business case.

## Slide 7: Project Product Description
Description – Develop an indicative business case justification to provide decision makers an early indication of the way forward.
Composition – Executive summary ; Reasons for undertaking the project; Business options ; Expected benefits ; Expected dis-benefits ; Timescale ; Costs ; Investment appraisal and major risks.
Derivation – Indicative business case (using Treasury’s guidance document) ; Business , user and regulatory requirements ; Efficiency and quality gains ; RFI process and vendor responses ; Project initiation document ; Procurement and finance guidance on total cost of ownership and RFI process ; Lessons learned from previous requirements, cost benefit justifications and investment logic mapping ; Risks and issues register.
Skills required – Expertise in stakeholder management and communications ; Expertise in project management and business analysis ; Expertise in medical certification business process ; Expertise in legal and regulatory aspects of medical certification ; Expertise in employee relations ; Expertise in finance, procurement and IT.
Quality Expectation – The indicative business case must be :
  Developed through robust analysis covering all key aspects of Treasury’s guidance document
  Aligned with the investment objectives already identified
Acceptance criteria and project level quality tolerances –
Priority 1 : Project recommends a preferred way forward and demonstrates the analysis performed even if there isn’t a case for change.
Priority 2 : Business, user and regulatory requirements fits with the investment objectives (i.e. anticipated efficiency and quality gains)
Priority 3 : External and internal stakeholders are appropriately engaged for the duration of the project
Priority 4 : RFI process conforms to the CAA’s procurement guidelines and government rules for sourcing
Priority 5 : Project costs must not exceed its budget allocation by 10%
Acceptance method –
Preliminary acceptance – Requirements are reviewed by a Senior User and an MIS Manager ; Approval of requirements by Project Executive ; RFI is reviewed by a Procurement, Legal, Finance and an MIS Manager ; Approval to initiate RFI process by Project Executive; Investment appraisal reviewed by CFO (or his delegate); Indicative business case reviewed and recommended by the project governance team and CFO (or his delegate); Approval of the indicative business case by Project Executive (or whosoever has the delegated financial authority);
Final acceptance – Approval of project closure report by the Project Executive.

## Slide 8: Roles
Chris Ford (Project Executive) is the accountable manager representing CAA interests monitoring the project at a strategic level, forming the project board and approving its membership, chairing board meetings , provides direction on risks and issues escalated, approving key documents and upward reporting to relevant groups.
John McKinlay (Manager – Personnel Flight & Training) is the accountable people manager representing the medical certification team and other associated teams and individuals that report to him. He will be consulted by the project on all matters concerning his team and will also communicate key messages and facilitate discussions with the concerned parties for the duration of the project.
Judi Te Huia (Senior User) represents the interests of users of the medical certification system and associated processes. She will provide the necessary resources to contribute to project products ; prioritise and resolve any contention in requirements; ensure requirements are accurate and aligned with the investment objectives; ensure business priorities are balanced with the delivery of project outcomes and provide guidance and recommendations to the project.
Dougal Watson (Principal Medical Officer) will be consulted as a subject matter expert from a medical perspective and will support Judi to ensure requirements are accurate and aligned with investment objectives.
Geoffrey Henderson (Project Manager) is responsible for preparing and managing the project in accordance with its plan ; engaging and managing stakeholders in conjunction with the project management team ; managing project budget, risks, issues and dependencies and product delivery.
Shiromani Samarkoon (Business Analyst) is responsible for the capture of business , user and regulatory requirements ; Contribute to the assessment of efficiency and quality gains with the project team ; development of the fit for purpose assessment and request for information (RFI) document and indicative business case in conjunction with Geoffrey Henderson and the project team.
Sio Tulia (Procurement Manager) will assure the integrity of the RFI process by reviewing the content of the RFI and provide guidance and recommendation to Chris Ford and Geoffrey Henderson
Paul La Planche (CFO) will review the content of the investment appraisal and provide guidance and recommendation to Chris Ford and Geoffrey Henderson or nominate a member of his team to do this on his behalf.
Arthur Devitt (CIO) will review the requirements and the content of the RFI and provide guidance and recommendation to Chris Ford and Geoffrey Henderson or nominate a member of his team to this on his behalf.

## Slide 9: Next Steps
Socialise the project approach
Develop a stakeholder engagement and communications plan
Socialise the stakeholder engagement plan
Develop a product breakdown
Estimate the effort and duration of the project
Draft the project plan (execution stage)
Socialise the project plan
Approve the project plan
Roles (Continued)
Lorraine Kilpatrick /Gemma Van Baarle (HR Advisors) will provide input to meet CAA’s obligations as a ‘good employer’ and guidance on a consistent approach to the management of change within the authority.
Michael Campbell, Diane Parker and Patrick Ryan (PSA Representatives) - The project will engage with PSA representatives from time to time and discuss project developments and progress.
John Sneyd (Chief Legal Counsel) will nominate team members to contribute to legal and regulatory aspects of medical certification and the commercial aspect of the RFI process.
Aviation Community Medical Liaison Group – The project will engage with members of this forum from time to time to discuss project developments and progress.

## Slide 10
Timelines
Duration of time allowed to deliver the following products ( October 31 - 9 weeks)
Planning ( 2 weeks)
Requirements (3 – 4 weeks)
Efficiency and quality gains (3 – 4 weeks)
Request for information ( 6 weeks)
Fit for purpose assessment ( 4 – 5 weeks)
Indicative business case (3 – 4 weeks)
Note: At this stage these are indicative timeframes and the operating assumption is that the schedule for these products overlap, the schedule will be confirmed when the project plan is baselined.
Scope
Basic online medical certification process requirements (67c) and the following as add-on requirements:
- Accredited medical conclusion and
- Section 27(h) and 27(i) of the Civil Aviation Act.

## Slide 11
Project Executive’s direction after the project is complete
Once this piece of work is complete the CAA’s next steps will be influenced by the following factors:
the availability or otherwise of off-the-self solutions to meet, either in whole or partially, the identified requirements;
consideration of the desirability of integrating this work with the planned replacement of the existing CAA suite of Aviation Safety Management System business systems, which do not currently include online medical functionality, and associated timing of this wider body of work;
completion of a business case providing a positive cost benefit with a return on investment over an acceptable period of time;
approval and allocation of funding;
alignment and possible integration with wider Government and Transport sector IT priorities and projects; and
the fit with the Government ICT Strategic and Action plan to 2017.