## Slide 1: National Airspace and Navigation Plan
Next Steps
Lisa Sheppard 13 August 2013

## Slide 2: Background
Technological changes
International response: ICAO, other States
  Global Navigation Plan and sub documents
  Other countries – NextGen (US) Single European Sky, Asia Pacific Seamless ATM Plan, plus individual countries
New Zealand response
  National Airspace Policy April 2011
  National Airspace and Navigation Plan
    8 cross sector working groups in navigation, surveillance, communications, information, ATM, Airspace, Aerodromes, Meteorological Services
    Completion of draft papers in each area June 2013

## Slide 3: Next Steps – Finishing the Plan
31 August: Internal and key stakeholder peer review
17 September: Ministerial approval for consultation
30 September – 30 November: Consultation, including workshops across the country
30 November: Detailed analysis of the proposed plan complete, including economic analysis, change management assessment and risk assessment
December-January – Authority approval of the final Plan and analysis
28 February 2014: Ministerial approval of the final Plan and on-going Implementation project

## Slide 4: Plan content
provide clear direction on the safe, cohesive, efficient and collaborative management of New Zealand’s airspace over the next decade
  Simplify language
  Develop overall objectives, principles and performance criteria
  Align chapters to same level of detail and structure
  Summary tables to integrate direction
  Analysis – technical and peer review, consultation, economic, risk analysis, change management analysis

## Slide 5: Peer review
  Overview tables provided today
  Full document provided for review by 15 August
  Individual meetings to identify key issues
  Industry overview workshop on 26 August
  Revised document provided 28 August (2 day turnaround)
Document ready for next stage (ministerial approval for Consultation) 31 August

## Slide 6: Key issues
When new ground and aircraft equipment upgrades will be required, and what airspace these requirements should apply to
What level of system redundancy should be provided via existing ground-based navigation aids
Human factors: procedural, training and cultural changes required
Diverse aircraft fleet, level of current equipage – how to make the transition
Capacity of the regulator, suppliers and engineers
How to address environmental issues that may result from technological changes
How to manage risks associated with change.